## Tickets
Key | Type | Summary | Description | Priority | Status | Sprint | Epic Link | Assignee | Reporter | Created | Resolved | Labels | Component
OMNI-1 | Epic | Order Management Core Build | Build the core order placement, status tracking, and cancellation capability in OmniBridge, including MongoDB persistence and API endpoints. | High | Done | Sprint 1 |  | Priya Nair | Elena Rodriguez | 2026-06-01 | 2026-06-12 | order-management | order-service
OMNI-2 | Epic | Oracle Middleware Integration | Integrate OmniBridge with Oracle Middleware (OIC) for order orchestration, including retries, circuit-breaking, and secure callback handling. | High | In Progress | Sprint 3 |  | Marcus Chen | Elena Rodriguez | 2026-06-15 |  | integration,oracle | oic-connector
OMNI-3 | Epic | MDM Master Data Sync | Establish product and customer master-data synchronization between OmniBridge and the Enterprise MDM Hub via REST pull and Kafka CDC events. | High | Done | Sprint 2 |  | Priya Nair | Elena Rodriguez | 2026-06-15 | 2026-06-26 | integration,mdm | mdm-connector
OMNI-4 | Story | Implement POST /api/v1/orders endpoint | As a shopper, I want to submit an order so that OmniBridge persists it and forwards it for fulfillment. | High | Done | Sprint 1 | OMNI-1 | Priya Nair | Elena Rodriguez | 2026-06-01 | 2026-06-08 | api | order-service
OMNI-5 | Story | Design orders collection schema in MongoDB | As a developer, I want a well-indexed orders schema (status, statusHistory, customerId) so queries and audit trails are efficient. | Medium | Done | Sprint 1 | OMNI-1 | Marcus Chen | Priya Nair | 2026-06-02 | 2026-06-09 | database | order-service
OMNI-6 | Story | Build oic-connector retry & circuit-breaker logic | As a system, I want failed calls to Oracle Middleware retried with exponential backoff and circuit-broken after repeated failures, so orders are never lost. | High | In Progress | Sprint 3 | OMNI-2 | Marcus Chen | Elena Rodriguez | 2026-06-29 |  | resilience | oic-connector
OMNI-7 | Story | Implement HMAC signature validation on OIC callback endpoint | As a security-conscious system, I want inbound Oracle Middleware status callbacks authenticated via HMAC signature so unauthorized callers are rejected. | High | In Progress | Sprint 3 | OMNI-2 | James Park | James Park | 2026-06-29 |  | security | oic-connector
OMNI-8 | Story | Build Kafka consumer for MDM CDC events | As a system, I want to consume MDM golden-record change events and update local caches so product/customer data stays fresh. | High | Done | Sprint 2 | OMNI-3 | Priya Nair | Elena Rodriguez | 2026-06-16 | 2026-06-24 | integration | mdm-connector
OMNI-9 | Story | Implement product cache fallback REST pull on cache miss | As a system, I want to fall back to a direct MDM Hub REST pull when a product/customer record is not in cache, so lookups never hard-fail. | Medium | To Do | Sprint 3 | OMNI-3 | Marcus Chen | Priya Nair | 2026-07-01 |  | resilience | catalog-service
OMNI-10 | Bug | Duplicate CDC events overwrite cache with stale data | mdm-connector applies out-of-order CDC events without checking mdmVersion, occasionally overwriting a newer cached record with an older one. | High | Closed | Sprint 2 | OMNI-3 | Priya Nair | Sarah Whitfield | 2026-06-20 | 2026-06-25 | data-integrity | mdm-connector
OMNI-11 | Bug | Order status not updating after Oracle callback timeout | When the OIC callback is delayed beyond the configured timeout, order status silently remains 'Received' with no retry or alert triggered. | High | In Progress | Sprint 3 | OMNI-2 | Marcus Chen | Sarah Whitfield | 2026-07-03 |  | reliability | oic-connector
OMNI-12 | Incident | Production outage — Oracle Middleware unreachable, order queue backlog | Sev-2 incident: Oracle Middleware was unreachable for 47 minutes on 2026-06-30, causing a backlog of ~1,200 orders stuck in 'Received' status. Resolved once connectivity was restored; retry queue drained automatically. | Highest | Resolved | N/A (Kanban) |  | David Okafor | Elena Rodriguez | 2026-06-30 | 2026-06-30 | incident,production | oic-connector
OMNI-13 | Incident | MongoDB Atlas cluster failover event | Sev-3 incident: Primary node failover occurred in the MongoDB Atlas replica set due to a cloud-provider maintenance event, causing ~90 seconds of elevated write latency. No data loss; automatic failover completed as designed. | Medium | Resolved | N/A (Kanban) |  | David Okafor | David Okafor | 2026-07-05 | 2026-07-05 | incident,infra | infra
OMNI-14 | Service Request | Provision read-only DB credential for QA team | QA team requires a least-privilege, read-only MongoDB credential scoped to the orders and product_cache collections for test verification. | Low | Closed | N/A (Kanban) |  | David Okafor | Sarah Whitfield | 2026-06-18 | 2026-06-19 | access-request | infra
OMNI-15 | Service Request | Rotate OAuth2 client secret for MDM Hub connector | Scheduled 90-day rotation of the mdm-rest-client OAuth2 client secret per the PAM Document rotation policy. | Medium | In Progress | N/A (Kanban) |  | James Park | James Park | 2026-07-08 |  | security,access-request | mdm-connector

## Sprints
Sprint | Start Date | End Date | Goal | Status | Tickets Included
Sprint 1 | 2026-06-01 | 2026-06-12 | Deliver core order management: submission, persistence, status API. | Completed | OMNI-1, OMNI-4, OMNI-5
Sprint 2 | 2026-06-15 | 2026-06-26 | Stand up MDM master-data sync (REST + Kafka CDC) and fix data-integrity issues found in testing. | Completed | OMNI-3, OMNI-8, OMNI-10
Sprint 3 | 2026-06-29 | 2026-07-10 | Harden Oracle Middleware integration: retries, circuit-breaking, callback security, and cache resilience. | Active (current) | OMNI-2, OMNI-6, OMNI-7, OMNI-9, OMNI-11