STATEMENT OF WORK

Omnichannel Inventory Intelligence Platform

Prepared for

Meridian Retail Group

Prepared by

Aurora Consulting Partners

Document Reference: SOW-MRG-2026-014

Version 1.0  |  Draft

July 9, 2026

SAMPLE / ILLUSTRATIVE DOCUMENT — FICTIONAL CLIENT AND FIGURES FOR DEMONSTRATION PURPOSES ONLY

# 1. Executive Summary

Meridian Retail Group (“Meridian” or “Client”) operates 214 stores across North America alongside a growing e-commerce channel. Store and online inventory are currently managed in separate systems, resulting in stockouts, overselling, and manual reconciliation work across merchandising, fulfillment, and store operations teams.

Aurora Consulting Partners (“Aurora” or “Consulting Team”) will design, build, and deploy an Omnichannel Inventory Intelligence Platform that unifies store and e-commerce inventory data, introduces AI-assisted demand forecasting, and provides real-time visibility to merchandising and store teams. This Statement of Work (“SOW”) defines the scope, deliverables, timeline, roles, and commercial terms for this engagement, issued under the Master Services Agreement between the parties dated January 15, 2026.

# 2. Business Objectives

- Reduce stockout-driven lost sales by providing real-time, unified inventory visibility across all channels.

- Cut manual inventory reconciliation effort in store operations by at least 60%.

- Improve demand forecast accuracy for top 500 SKUs using AI-assisted forecasting models.

- Establish a reusable data and integration foundation to support future omnichannel initiatives (e.g., ship-from-store, buy-online-pickup-in-store expansion).

# 3. Scope of Work

## 3.1 In Scope

- Discovery and current-state assessment of existing POS, warehouse management, and e-commerce inventory systems.

- Design and implementation of a unified inventory data layer integrating store POS, warehouse management system (WMS), and e-commerce platform.

- AI-assisted demand forecasting module covering the top 500 SKUs by revenue.

- Real-time inventory dashboard for merchandising, store operations, and fulfillment teams.

- Integration with existing store replenishment workflows.

- User acceptance testing (UAT) support and defect resolution.

- Knowledge transfer and documentation for Meridian's internal IT team.

## 3.2 Out of Scope

- Physical hardware procurement or installation (e.g., in-store scanners, RFID tags).

- Changes to Meridian's point-of-sale (POS) software beyond required integration endpoints.

- Support for international store locations outside North America.

- Post-go-live managed services beyond the 30-day hypercare period defined in Section 6.

# 4. Deliverables

| # | Deliverable | Description | Format |
| --- | --- | --- | --- |
| D1 | Current-State Assessment Report | Findings from discovery, including system inventory, data quality gaps, and integration risks. | Document |
| D2 | Solution Design Document | Target architecture, data model, integration design, and forecasting model approach. | Document |
| D3 | Unified Inventory Data Layer | Configured and deployed integration between POS, WMS, and e-commerce platform. | Software |
| D4 | AI Demand Forecasting Module | Trained and validated forecasting model for top 500 SKUs, with retraining pipeline. | Software |
| D5 | Inventory Visibility Dashboard | Role-based dashboard for merchandising, store ops, and fulfillment teams. | Software |
| D6 | UAT Summary & Defect Log | Results of user acceptance testing and resolution status of identified defects. | Document |
| D7 | Training & Handover Package | Admin guide, runbooks, and recorded training sessions for Meridian IT. | Document / Video |

# 5. Project Approach & Methodology

The engagement will be delivered in four phases using an agile delivery approach with two-week sprints. Aurora will use IBM Consulting Advantage and Bob-assisted development practices internally to accelerate solution design, code generation, testing, and documentation throughout Phases 2 and 3; this does not change Client-facing deliverables or acceptance criteria.

| Phase | Name | Key Activities | Duration |
| --- | --- | --- | --- |
| 1 | Discovery & Design | Current-state assessment, requirements workshops, target architecture and data model design. | 3 weeks |
| 2 | Build | Data layer integration, forecasting model development, dashboard build. | 8 weeks |
| 3 | Test & Stabilize | System integration testing, UAT support, defect resolution, performance tuning. | 3 weeks |
| 4 | Deploy & Hypercare | Production go-live, 30-day hypercare support, training and handover. | 4 weeks |

# 6. Timeline & Milestones

| Milestone | Target Date | Acceptance Trigger |
| --- | --- | --- |
| M1 – Discovery Complete | Aug 7, 2026 | Client sign-off on Current-State Assessment Report (D1). |
| M2 – Design Approved | Aug 28, 2026 | Client sign-off on Solution Design Document (D2). |
| M3 – Build Complete | Oct 23, 2026 | Data layer, forecasting module, and dashboard deployed to staging. |
| M4 – UAT Sign-off | Nov 13, 2026 | Client sign-off on UAT Summary (D6). |
| M5 – Go-Live | Nov 27, 2026 | Production deployment complete; hypercare period begins. |
| M6 – Engagement Close | Dec 25, 2026 | Hypercare complete; Training & Handover Package (D7) accepted. |

# 7. Roles & Responsibilities

| Role | Organization | Responsibility |
| --- | --- | --- |
| Engagement Sponsor | Meridian | Overall accountability for business outcomes; escalation point for scope or budget decisions. |
| Product Owner | Meridian | Prioritizes backlog, approves designs, participates in sprint reviews and UAT. |
| Engagement Partner | Aurora | Overall delivery accountability; primary relationship owner. |
| Delivery Lead | Aurora | Day-to-day delivery management, sprint planning, status reporting. |
| Solution Architect | Aurora | Owns target architecture and integration design. |
| Data Scientist(s) | Aurora | Develops and validates the demand forecasting model. |
| IT Systems Owner | Meridian | Provides access to POS, WMS, and e-commerce systems; supports environment setup. |

# 8. Assumptions & Dependencies

- Meridian will provide timely access to POS, WMS, and e-commerce test environments within 5 business days of contract signature.

- Meridian will make the Product Owner and IT Systems Owner available for a minimum of 8 hours per week throughout the engagement.

- Historical sales data (minimum 24 months) for the top 500 SKUs will be made available in a structured, exportable format.

- Any delay in Client-provided access, data, or approvals of more than 5 business days may result in a corresponding adjustment to the timeline in Section 6.

- All third-party software licensing (cloud hosting, forecasting platform runtime) is the responsibility of the Client unless otherwise agreed in writing.

# 9. Application Security

Given the platform's access to POS transaction data and integration touchpoints across three production systems, Aurora will apply the IBM Consulting Cybersecurity Services Digital AppSec Champion (DASC) methodology during solution design, covering: data flow and access-control review across the integration layer, secure handling of any AI-agent-assisted code generation and internal tooling used during Phase 2, and validation that role-based dashboard access enforces least-privilege by user role. Findings and remediations will be documented in a DASC Security Review Summary, delivered alongside D2 (Solution Design Document).

# 10. Acceptance Criteria

Each deliverable in Section 4 will be reviewed by the Client's Product Owner within 5 business days of submission. Deliverables will be deemed accepted if no written objection specifying material, documented non-conformance with the applicable requirements is received within that window. Acceptance of a deliverable does not waive Aurora's obligation to remediate defects identified during subsequent testing phases.

# 11. Change Management

Any request to modify scope, deliverables, timeline, or fees defined in this SOW will be documented in a Change Request (CR) describing the change, impact on timeline and fees, and required approvals. No change will be implemented until the CR is signed by both parties' Engagement Sponsors.

# 12. Commercial Terms

| Phase | Fee (USD) | Billing Trigger |
| --- | --- | --- |
| Phase 1 – Discovery & Design | $180,000 | Upon Client sign-off of M2 (Design Approved). |
| Phase 2 – Build | $420,000 | 50% upon Phase 2 kickoff; 50% upon M3 (Build Complete). |
| Phase 3 – Test & Stabilize | $140,000 | Upon Client sign-off of M4 (UAT Sign-off). |
| Phase 4 – Deploy & Hypercare | $110,000 | Upon M6 (Engagement Close). |
| Total | $850,000 |  |

Fees exclude applicable taxes and any pre-approved travel expenses, which will be billed at cost with prior written approval. Payment terms are net 30 days from invoice date, per the Master Services Agreement.

# 13. Signatures

By signing below, the parties agree to the scope, deliverables, timeline, and commercial terms set out in this Statement of Work.

For Meridian Retail Group

Name / Title / Date

For Aurora Consulting Partners

Name / Title / Date